ZAHY

Partner Platform

Team Operating Manual & Project Plan

How the team works together • Per-role SOPs • AI-assisted (Cursor) workflow • Phased delivery

Companion to the Architecture & Build Plan (v2) and SRS-1

Time Solution — Zahy Platform  •  Version 1.0  •  June 2026

# Contents

# 1. Purpose & How to Use This

This manual defines how the Zahy Partner Platform team works together: the shared operating rules, each role's standard operating procedure (SOP), the AI-assisted development workflow with Cursor, and the phased project plan. It assumes a small, senior, AI-leveraged team and is designed to keep everyone aligned to a single source of truth: the approved BRD, Architecture & Build Plan, SRS and SDD documents.

Golden rule: the documents are the source of truth. Code implements the documents; it does not invent scope. If reality and a document disagree, raise it, decide, and update the document — do not silently diverge.

# 2. Team & Responsibilities

| Role | Count (start → full) | Owns |
| --- | --- | --- |
| CTO / Technical Founder | 1 | Vision, priorities, investor/partner relationships, final call on trade-offs |
| Architect / Tech Lead | 1 | Module design, contracts/ACL over Commerce, standards, code review |
| Backend Engineer (.NET/ABP) | 1 → 2–3 | Identity, Partner Platform, Webhook Hub, CDC, commission, connectors |
| Frontend Engineer (Angular) | 1 → 2 | Admin console, Partner Portal, dashboard, Web POS |
| UI/UX Designer | ½ → 1 | Design system, RTL Arabic, partner/admin/POS flows |
| DevOps / Infra | ½ → 1 | KSA hosting, CI/CD, GitHub, secrets, environments |
| QA / Test | ½ → 1 | Acceptance testing, connector integration testing |

Note: the CTO role is initially covered by the technical founder + architect; hire a dedicated CTO when the team passes ~6–8 people or for fundraising. Backend is the critical path — invest there first.

# 3. Shared Operating Rules

## 3.1 Source of truth & change control

- The BRD / Architecture / SRS / SDD are authoritative. New scope starts as a document change, not a surprise PR.

- Material technical decisions are recorded as short ADRs (one page: context, decision, consequences).

## 3.2 Repository & branching

- One GitHub repository under the Time-solution organisation; trunk-based with short-lived feature branches.

- Branch naming: feature/<ticket-id>-short-desc, fix/<ticket-id>-... . No direct commits to main.

- Every change goes through a Pull Request; main is always releasable.

## 3.3 Pull requests & code review

- PRs are small and single-purpose; link the ticket and the SRS/SDD requirement ID.

- At least one reviewer; the Architect reviews anything touching identity, contracts, security or money (commission/payouts).

- No PR merges without passing CI (build + tests + lint) and a green review.

## 3.4 Definition of Ready / Done

| Definition of Ready (to start) | Definition of Done (to merge) |
| --- | --- |
| Linked to an SRS/SDD requirement; acceptance criteria clear; dependencies known; design/API agreed. | Acceptance criteria met; tests written & passing; reviewed; no secrets in code; docs/ADR updated; deployed to staging. |

## 3.5 Security rules (non-negotiable)

- No secrets, tokens or connection strings in code or commits — use the secret store. Remediate the previously found exposed secrets before any partner API is exposed.

- Never modify, fork or decompile the compiled makookapp packages (Commerce, Promotions, Shipping.Oto).

- Tenant isolation is enforced on every data access; partner access is scoped and audited.

## 3.6 Communication cadence

| Ceremony | When | Purpose |
| --- | --- | --- |
| Daily stand-up (15 min) | Daily | Yesterday / today / blockers |
| Sprint planning | Start of sprint (2 wks) | Pull SRS items into the sprint |
| Backlog refinement | Mid-sprint | Clarify next items to Ready |
| Sprint review + demo | End of sprint | Demo to founder; accept against criteria |
| Retrospective | End of sprint | Improve the process |
| Architecture sync | Weekly | Decisions, ADRs, cross-cutting concerns |

# 4. Per-Role SOPs

## 4.1 CTO / Technical Founder

Mission: Set direction, protect priorities, and own the trade-offs others cannot.

- Owns the roadmap and phase priorities; approves scope changes and ADRs with business impact.

- Holds partner/contractor relationships (incl. pursuing makookapp source delivery in parallel).

- Runs the sprint review as the accepting stakeholder; unblocks decisions within 24h.

- Cursor: reviews AI-generated architecture proposals; does not merge code directly.

## 4.2 Architect / Tech Lead

Mission: Guard the architecture and the boundaries; make the system coherent.

- Owns module design, the contracts/Anti-Corruption Layer over Commerce, and the webhook-based integration design.

- Defines coding standards, the .cursor rules file, and the PR review bar.

- Mandatory reviewer for identity, security, contracts, and commission/payout code.

- Writes ADRs; keeps the SDD current; resolves cross-cutting technical disputes.

- Cursor: authors the standard build prompts and the repo rules; spot-checks AI output for boundary violations.

## 4.3 Backend Engineer (.NET / ABP)

Mission: Build the owned core safely and on the contracts — identity, platform, webhooks, money.

- Implements per the SRS/SDD: Identity (OpenIddict), Partner Platform, Webhook Hub, CDC → Order Ledger, commission engine, connectors.

- Programs against owned contracts/interfaces, never against compiled internals.

- Writes unit + integration tests for every endpoint; ensures idempotency on webhook/CDC handlers.

- Cursor: plan-then-build; small diffs; runs the read-only audit before changing shared areas; never lets Cursor touch compiled packages or secrets.

## 4.4 Frontend Engineer (Angular)

Mission: Deliver fast, RTL-correct, role-aware interfaces for admin, partner and POS.

- Builds the admin console, Partner Portal, dashboard surfacing and Web POS to the design system.

- Implements permission-gated routes against the IdP; handles the POS polling + accept/reject SLA UI.

- Ensures Arabic RTL correctness and English parity; no business logic in the UI that belongs server-side.

- Cursor: uses the frontend design tokens; generates components then reviews for accessibility and RTL.

## 4.5 UI/UX Designer

Mission: Make the flows obvious and the platform feel like one product.

- Owns the design system, component library, and RTL Arabic patterns.

- Designs partner onboarding, admin approval, dashboard and POS order flows before build.

- Hands off specs/tokens the frontend can implement directly; reviews built screens.

## 4.6 DevOps / Infra

Mission: Keep the pipeline green and the platform inside KSA and secure.

- Sets up GitHub, CI/CD, environments (dev/staging/prod), and the secret store.

- Provisions KSA hosting (target: Google Cloud Dammam via CNTXT); manages CDC access and DB backups.

- Owns monitoring, webhook delivery dashboards/DLQ alerts, and release automation.

## 4.7 QA / Test

Mission: Prove each requirement is met before the founder sees it.

- Turns SRS acceptance criteria into test cases; verifies before sprint review.

- Owns connector integration testing (Jahez/HungerStation sandbox, 3PL, carrier) and the 5-minute SLA path.

- Maintains a regression suite; signs off the Definition of Done.

# 5. Cursor / AI-Assisted Development SOP

Cursor is the team's primary implementation accelerator. To keep AI output safe and consistent, everyone follows the same workflow and the repo carries a shared rules file.

## 5.1 Standard workflow

- Pick a ticket linked to an SRS/SDD requirement (Definition of Ready met).

- Run a read-only audit prompt first when touching shared/unknown areas — understand before changing.

- Ask Cursor to produce a short plan; review the plan before any code.

- Implement in small diffs; keep each change reviewable.

- Require tests in the same change; run them locally.

- Open a PR; never merge AI output unreviewed.

## 5.2 Hard guardrails for AI output

- Never modify, fork or decompile the compiled makookapp packages.

- Never write secrets/connection strings into code; use the secret store.

- Never write directly to Commerce tables; reads are read-only (CDC) and writes go through owned services/contracts.

- Integration between components is via webhooks, not an internal event bus.

- All new data access respects tenant isolation.

## 5.3 Repo rules file

A shared .cursor rules file (provided alongside this manual) encodes the stack, the guardrails above, naming conventions, and the plan-then-build discipline so every team member's Cursor behaves the same. The Architect owns it; changes go through PR like code.

## 5.4 Standard prompt shape

- Context: which module, which SRS/SDD requirement ID.

- Mode: read-only audit, or plan-then-build.

- Constraints: the guardrails (no compiled packages, no secrets, webhooks not event bus, tenant isolation).

- Deliverable: small diff + tests; stop for review before merge.

# 6. Project Plan — Phases & Milestones

Phases follow the Architecture & Build Plan. Durations are indicative in two-week sprints and depend on final team size; Phases 0–3 sit in core Zahy and touch no compiled package.

| Phase | Name | Primary owners | Exit criteria | Indic. |
| --- | --- | --- | --- | --- |
| 0 | Preparation | Architect, DevOps | Repo + CI/CD live; secrets remediated; CDC access; versions confirmed | 1 spr |
| 1 | Owned Identity | Backend, Architect | SSO login for all scopes; admin login; roles; tokens | 2–3 spr |
| 2 | Webhook Hub | Backend | Signed delivery + outbox + retries + DLQ + logs | 2 spr |
| 3 | Isolation + Order capture | Backend, Architect | ACL over contracts; CDC → Order Ledger working | 2 spr |
| 4 | Partner Platform foundation | Backend, Frontend | Onboarding + lifecycle; dashboard surfacing | 2–3 spr |
| 5 | Commission & Billing | Backend | Composable rules; subscription/transaction/hybrid | 2 spr |
| 6 | Connectors + Aggregators | Backend, Frontend, QA | Jahez + HungerStation live; POS polling + SLA | 3–4 spr |
| 7 | Fulfilment + Carriers | Backend, QA | 3PL + carrier adapters; inventory reconcile; returns | 2–3 spr |
| 8 | Settlement + Admin | Backend, Frontend | Payouts + ZATCA; full admin console | 2 spr |
| 9 | AI Agent (parallel) | Backend, Frontend | Per AI Agent BRD | parallel |

# 7. How a Feature Flows (Collaboration Workflow)

- SRS requirement → SDD design (Architect) → design/API agreed.

- Ticket created with acceptance criteria (Definition of Ready).

- Designer provides screens/tokens (if UI); API contract fixed (if backend).

- Engineer builds in Cursor (plan-then-build, small diffs, tests).

- PR → review (Architect for sensitive areas) → CI green → merge.

- Deploy to staging → QA verifies acceptance criteria.

- Sprint review demo → founder accepts → release.

Parallelism: backend and frontend work the same feature against an agreed API contract so they progress in parallel; the designer stays one step ahead of the frontend; DevOps and QA support across all streams.

# 8. Risks & Guardrails

| Risk | Guardrail / Mitigation |
| --- | --- |
| Dependence on compiled makookapp packages | Isolate via contracts; pursue source delivery in parallel; never modify the binaries |
| Exposed secrets | Remediate before any partner API; secret store; secret-scanning in CI |
| Unreviewed AI output | Plan-then-build; small PRs; mandatory review; tests required |
| Commission/money errors | Architect review on all money code; append-only ledger; idempotency |
| Aggregator 5-minute SLA misses | Short-interval POS polling + countdown + alert; QA owns this path |
| Scope drift | Documents are source of truth; changes via ADR/doc update |

# 9. Getting Started Checklist

- Create the GitHub repo under Time-solution; add the team; protect main.

- Drop in the provided .cursor rules file; connect Cursor to the repo.

- Stand up CI/CD, environments and the secret store (DevOps).

- Confirm namespaces (Zahy.* / App.* / Tajer.*) and ABP + Angular versions.

- Run Phase 0, then begin Phase 1 (Owned Identity) with the build prompt.

Use alongside the .cursor rules file provided. Next deliverable: Solution Design (SDD) for Increment 1, then the Phase-1 Cursor build prompt.